## CC1_ZW
Modular Project/ISAS Allocation/Evaluation
Trainer |  |  |  |  | Batch# CC1 | Weekly Progress Report | [23 empty] | Remarks
Student Details | [5 empty] | Week 1 |  |  |  | Week 2 |  |  |  | Week 3 |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6
[6 empty] | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking
SrNo | School ID | Name (Chinese) | English Name | Team Leader | Project Title
1 | 12018245753 | 马洋 | Carrol | 马洋 | Student Management System
2 | 12018245759 | 苏庆 | Luella
3 | 12018245772 | 朱文华 | Wesley
4 | 12018245785 | 何龙坤 | Hart
5 | 12018245851 | 何文亮 | Hans | 王丹阳 | Examination Portal
6 | 12018246051 | 刘伯城 | Lionel
7 | 12018246053 | 王丹阳 | Ella
8 | 12018246054 | 张俊 | May
9 | 12018246059 | 李国龙 | Charles | 李国龙 | Restaurant Management System
10 | 12018246063 | 韩亚州 | Casey
11 | 12018246070 | 魏嘉李 | Christy
12 | 12018246079 | 张娜娜 | Ann
13 | 12018246082 | 张东顺 | Dietrich | 张东顺 | Student Feedback System
14 | 12018246084 | 哈烨坤 | Aaron
15 | 12018246091 | 丁源 | Michael
16 | 12018246094 | 李逸凡 | Clear
17 | 12018246098 | 张嘉颖 | Yami | 张嘉颖 | Restaurant Management System
18 | 12018246102 | 贾宁辉 | Alan
19 | 12018246103 | 周莉 | Judy
20 | 12018246106 | 马月兰 | Amy
21 | 12018246109 | 滕国瑞 | Snake | 宋晓强 | Shopping Portal
22 | 12018246110 | 宋晓强 | Athy
23 | 12018246112 | 胡新兵 | Tom
24 | 12018246115 | 杨玄 | Bryant
25 | 12018246121 | 康金虎 | Jackson | 李博 | Shopping Portal
26 | 12018246124 | 李博 | Second
27 | 12018246125 | 祁慧东 | Harry
28 | 12018246127 | 双雅婷 | Una
29 | 12018246129 | 杨宁 | Jack | 杨宁 | Student Management System
30 | 12018246135 | 邹业妮 | Denise
31 | 12018246136 | 薛永帅 | Jerry
32 | 12018246137 | 杨皓 | Ethan
33 | 12018246140 | 夏霄 | Abe | 王艳宁 | Hospital Management System
34 | 12018246142 | 李娜 | Lena
35 | 12018246150 | 王艳宁 | Grance
36 | 12018246159 | 李伟 | Albert
37 | 12018246160 | 虎辉 | Evan | 康静 | Student Feedback System
38 | 12018246164 | 王万文 | James
39 | 12018246166 | 罗磊 | Andolf
40 | 12018246169 | 康静 | Rain
41 | 12017245655 | 虎登发 | Gorden | 田嘉喜 | Examination Portal
42 | 12016246281 | 田嘉喜 | Dream
43 | 12017245779 | 李嘉鹏 | Niko
备注： | 12018246140 | 夏霄 | Abe | 当兵

## CC2_ZW
Modular Project/ISAS Allocation/Evaluation
Trainer |  |  |  |  | Batch# CC2 | Weekly Progress Report | [23 empty] | Remarks
| Student Details |  |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1
SrNo | School ID | Name (Chinese) | English Name | Team Leader | Project Title | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking
1 | 12018246052 | 万军 | Tobey | 万军 | Shopping Portal
2 | 12018246055 | 刘丹莉 | Eva
3 | 12018246056 | 邓博文 | Stark
4 | 12018246057 | 李涛 | Melinda
5 | 12018246058 | 万里倩 | Foam | 万里倩 | Restaurant Management System
6 | 12018246060 | 杨隆 | Alan
7 | 12018246062 | 马嘉龙 | Dan
8 | 12018246068 | 郭瑜麟 | Angelina
9 | 12018246075 | 连源 | Melody | 高雪 | Hospital Management System
10 | 12018246076 | 王鹏 | Spike
11 | 12018246077 | 曾玉洁 | Shiny
12 | 12018246080 | 高雪 | Emily
13 | 12018246086 | 马姝昱 | Sara | 杨昊 | Examination Portal
14 | 12018246090 | 王紫瑜 | Miranda
15 | 12018246093 | 刘德鹏 | Devin
16 | 12018246096 | 杨昊 | Eric
17 | 12018246097 | 马佳华 | D.Rose | 雷凯 | Student Management System
18 | 12018246117 | 陈嘉炜 | Park
19 | 12018246118 | 雷凯 | Karry
20 | 12018246119 | 王鑫峰 | Gene
21 | 12018246120 | 牛涛 | Saber | 陈家辉 | Shopping Portal
22 | 12018246122 | 陈建 | Cope
23 | 12018246130 | 张爱国 | George
24 | 12018246131 | 陈家辉 | Ann
25 | 12018246134 | 马世发 | Edam | 张一博 | Restaurant Management System
26 | 12018246138 | 王嫣 | Lilly
27 | 12018246139 | 张一博 | Kevin
28 | 12018246144 | 王恺 | Thor
29 | 12018246147 | 杨博 | Bert | 杨博 | Hospital Management System
30 | 12018246149 | 杨起帆 | Alina
31 | 12018246152 | 张龙龙 | Dunte
32 | 12018246153 | 马明虎 | Derrick
33 | 12018246157 | 李旭通 | Patrick | 张慧霞 | Student Feedback System
34 | 12018246158 | 胡安宁 | Jennifer
35 | 12018246161 | 张慧霞 | Teresa
36 | 12018246162 | 王晓斌 | Breeze
37 | 12018246167 | 谢安国 | Carson | 杨文源 | Shopping Portal
38 | 12017245812 | 赵连杰 | Kim
39 | 12017245817 | 史雲霄 | Stark
40 | 12017245796 | 杨文源 | Kelent

## CC3_ZW
Modular Project/ISAS Allocation/Evaluation
Trainer |  |  | Batch# CC3 |  |  | Weekly Progress Report | [23 empty] | Remarks
| Student Details |  |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1
SrNo | School ID | Name (Chinese) | English Name | Team Leader | Project Title | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking
1 | 12018246099 | 赵恬欣 | Elizabeth | 赵恬欣 | restaurant managent system
2 | 12018246148 | 张盼风 | Maria
3 | 12018246105 | 苏嘉轩 | Mike
4 | 12018246067 | 李兴旺 | Lee
5 | 12018246072 | 禹杰 | Jerry
6 | 12018246071 | 田宗宝 | Terrel | 王新文 | examination protal
7 | 12018246111 | 王新文 | David
8 | 12018246146 | 姬委 | Jameson
9 | 12018246154 | 樊启启 | Jayden
10 | 12018246126 | 刘晗 | Lawis | 刘晗 | student managent system
11 | 12018246113 | 景芮楠 | Renee
12 | 12018246107 | 李付迁 | Lisa
13 | 12018246168 | 庞卓 | Katy
14 | 12018246141 | 卢柱 | Kobe
15 | 12018246095 | 朱振 | Alex | 王巍 | student feedback system
16 | 12018246155 | 于静龙 | Young
17 | 12018246548 | 王巍 | Bob
18 | 12018246165 | 高万富 | Adam
19 | 12018246163 | 王荣霞 | Jennifer | 王漫 | student managent system
20 | 12018246104 | 王漫 | Carry
21 | 12018246069 | 杨林凯 | Suzy
22 | 12018246151 | 陈芮 | Selina
23 | 12018246087 | 胡聪山 | Henry | 胡阿慧 | shopping portal
24 | 12018246083 | 胡阿慧 | Alisa
25 | 12018246073 | 虎娜 | Fern
26 | 12018245775 | 虎小贵 | Bron
27 | 12018246108 | 冯新胜 | Addie | 冯新胜 | hospital managent system
28 | 12018246133 | 田进虎 | James
29 | 12018246061 | 范嘉慧 | Bob
30 | 12018246089 | 路佳轩 | Aimee
31 | 12017245858 | 周佳宁 | Potter | 赵少华 | student feedback system
32 | 12018246065 | 徐旺 | Richard
33 | 12018246078 | 秦轲 | Candy Boy
34 | 12017245867 | 赵少华 | Raymond
35 | 12018246092 | 牛健峰 | Haley | 徐斌 | restaurant managent system
36 | 12018246100 | 徐斌 | Alexander
37 | 12018246101 | 贺海龙 | Harden
38 | 12018246074 | 胡瑞铎 | Jason
备注： | 12018246114 | 杨彦曦 | Jack | 休学

## NIIT1_ZW
Modular Project/ISAS Allocation/Evaluation
Trainer |  |  | Batch# NIIT1 |  |  | Weekly Progress Report | [23 empty] | Remarks
Student Details | [5 empty] | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1 |  |  |  | Week 1
SrNo | School ID | Name (Chinese) | English Name | Team Leader | Project Title | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking
1 | 12018246252 | 孙付贵 | Alex | 孙付贵 | restaurant managent system
2 | 12018246233 | 张祺之 | Ellison
3 | 12018246261 | 李登龙 | Jerry
4 | 12018246267 | 孙虎威 | Larry
5 | 12018246262 | 张翻弟 | Joanna | 张翻弟 | student managent system
6 | 12018246232 | 刘小芳 | Amy
7 | 12018246220 | 申梦芸 | Adele
8 | 12018246204 | 李晨航 | Kyrie
9 | 12018246235 | 买小芳 | Summer | 鲜少玉 | hospital managent system
10 | 12018246269 | 王亚男 | Angela
11 | 12018246244 | 张永强 | Zed
12 | 12018246268 | 鲜少玉 | Robertson
13 | 12018246207 | 贺炜桐 | Lucky | 贺炜桐 | shopping portal
14 | 12018246210 | 张琰翊 | Lily
15 | 12018246265 | 刘娜娜 | Luna
16 | 12018246222 | 李婷婷 | Iris
17 | 12018246255 | 马瑞虎 | Andy | 张旦东 | shopping portal
18 | 12018246201 | 张旦东 | Elvis
19 | 12018246238 | 梁娜 | Quella
20 | 12018246212 | 黄川 | Pyke
21 | 12017246053 | 蔡国栋 | Jack Cai
22 | 12018245934 | 陈昭君 | Mia | 王炳刚 | student managent system
23 | 12018245921 | 王萍 | Sunny
24 | 12018245917 | 柴潇凤 | Tina
25 | 12018245948 | 王炳刚 | WZZ
26 | 12018246225 | 王志龙 | James | 陈辉 | hospital managent system
27 | 12018246221 | 孙强 | Eli
28 | 12018246241 | 赵浩 | Wosage
29 | 12018246208 | 陈辉 | Moore
30 | 12018246227 | 王志行 | Sam | 尹海云 | examination protal
31 | 12018246215 | 尹海云 | Ibiza
32 | 12018246223 | 张骞 | Irving
33 | 12017246001 | 段家宝 | Bazinga
34 | 12018246257 | 卢莉伟 | Luse | 卢莉伟 | student feedback system
35 | 12018246263 | 杨彦芃 | Sunshine
36 | 12018246217 | 李九江 | Lisege
37 | 12018246219 | 王超磊 | Edward
38 | 12018246206 | 王凯琪 | Kathy

## NIIT2_ZW
Modular Project/ISAS Allocation/Evaluation
Trainer |  |  | Batch# NIIT2 |  |  | Weekly Progress Report | [23 empty] | Remarks
Student Details | [5 empty] | Week 1 |  |  |  | Week 2 |  |  |  | Week 3 |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  | Week 6
[6 empty] | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking | DB Design | UI Design | Functionality | Error Checking
SrNo | School ID | Name (Chinese) | English Name | Team Leader | Project Title
1 | 12018246231 | Carl | 刘丛林 | Gavin | Student Management System |  |  | 构思 |  | 创建数据库 |  |  |  |  | 实现 | [5 empty] | 改错 |  |  | 完成
2 | 12018246250 | Gavin | 马小龙 |  |  |  |  | 构思 |  |  |  | 设计框架 |  |  |  | 实现 |  |  |  |  | 改错 |  | 完成
3 | 12018243770 | Sam | 马宏 |  |  |  |  | 构思 |  |  |  | 设计框架 |  | 实现 | [6 empty] | 改错 | 完成
4 | 12018245904 | Charles | 王启宏 | [26 empty] | Army
5 | 12018246260 | Susan | 虎园凤 | Susan | Student Management System | 数据库的设计 |  |  |  | 创建数据库 |  |  |  | 表的设计 |  |  |  | 创建表 |  |  |  | 插入数据 |  |  |  | 完成
6 | 12018246264 | Belinda | 周苗苗 |  |  |  | 登陆界面 |  |  |  | 学生主页 |  |  |  | 教师主页 |  |  |  | 学生详细信息界面 |  |  |  | 教师详细信息界面 |  |  |  | 完成
7 | 12018246249 | Jerry | 周李牧野 |  |  |  |  | 实现登录 |  |  |  | 界面跳转 |  |  |  | 界面跳转 |  |  |  | 实现导航 |  |  |  | 实现导航 |  |  |  | 完成
8 | 12018246254 | Kirito | 李磊 | [5 empty] | 连接数据库 |  |  |  | 连接数据库 |  |  |  | 实现插入 |  |  |  | 实现查询 |  |  |  | 实现修改 |  |  |  | 完成
9 | 12018246216 | Wilson | 唐俊杰 | Wilson | Hospital Management System |  |  |  |  | Design of doctor table | [11 empty] | 完成
10 | 12018246209 | Raven | 马富彪 | [10 empty] | Patient table design | [8 empty] | 完成
11 | 12018246256 | Vickie | 谢浩 | [14 empty] | Overall design database | [5 empty] | 完成
12 | 12018246228 | Smith | 万龙 |  |  |  | Main page |  |  | Doctor page |  |  |  |  | Patient page |  |  |  | Login page | [5 empty] | 完成
13 | 12018246246 | Enzo | 王宜轩 | Enzo | Shopping Portal | [9 empty] | login interface |  |  | Interface links |  |  |  |  | Interface optimization
14 | 12018246266 | Glasses | 兰志成 | [10 empty] | Table building |  |  |  | database |  |  |  |  | database
15 | 12018246237 | Walker | 王维文 |  |  |  | Category page |  |  |  | Category page | [6 empty] | Interface links |  |  |  |  | Interface optimization
16 | 12018246270 | Roy | 晁显 |  |  |  | Total Page |  |  |  | Category page | [6 empty] | Interface links |  |  |  |  | Interface optimization
17 | 12018246218 | Kyrie | 郭晓鹏 | Kyrie | Student Feedback System |  | teacher page |  |  |  | teacher page |  |  |  | teacher page |  |  | create table |  |  |  | 完成
18 | 12018246236 | Vincent | 马虎 |  |  |  | student page |  |  |  | student page |  |  |  | student page |  |  | create table |  |  |  |  | 完成
19 | 12018246253 | Kyle | 潘文伯 |  |  |  | home page |  |  |  | home page |  |  |  | home page |  |  | create table | [5 empty] | 完成
20 | 12018246248 | Garland | 郭斌 |  |  |  | login page |  |  |  | login page |  |  |  | login page |  |  | create table | [6 empty] | 完成
21 | 12018246247 | Linda | 陈惠兄 | Linda | Examination Portal |  | Login page |  |  |  | Success page |  |  |  | Exam page |  |  |  | Exam page |  |  |  | Student exam information |  |  | 完成
22 | 12018246226 | Linna | 金丽娜 |  |  |  | Home page、create database |  |  |  | Student page |  |  |  | Teacher page |  |  |  | Course of teach |  |  |  | Student exam information |  |  |  | 完成
23 | 12018246239 | Tom | 马锦秀 | [14 empty] | create table |  |  |  | database | [5 empty] | 完成
24 | 12018246213 | Jack Yu | 禹鹏强 | [26 empty] | Army
25 | 12018246242 | Abby | 郭君 | Abby | Restaurant Management |  | Design Table |  |  |  | Create user table |  |  |  | Create register table |  |  | create table | Create food table |  |  | database | Database |  |  | 完成
26 | 12018246258 | Keira | 姬云利 |  |  |  | Design Login Page |  |  |  | Create Login Page |  |  |  | Design desert page |  |  |  | Create desert page |  |  |  | Design Baozai page |  |  |  | 完成
27 | 12018246229 | Sunny | 麻建萍 |  |  |  | Design Register |  |  |  | Create Register |  |  |  | Design drink page |  |  |  | create drink page |  |  |  | Create Baozai page |  |  |  |  | 完成
28 | 12018246224 | Angle | 赵欣 |  |  |  | Design Home |  |  |  | Create Home |  |  |  | Design Noddle page |  |  |  | create noodle page |  |  |  | Add details | [5 empty] | 完成
29 | 12018246214 | Sean | 王政国 | Sean | Hospital Management System |  | Model page |  |  |  | Hospital home page |  |  |  | Register page |  |  | create table | Intergration of all page |  |  | create table |  | Add data |  | 完成
30 | 12018246230 | Clear | 王嘉俊 |  |  |  | Login page |  |  |  | Success page | [5 empty] | check all page bug | create table |  | Link |  | create table |  | query data |  |  | 完成
31 | 12018246202 | Gerry | 杨军 |  |  |  | Doctor Home page |  |  |  | Doctor page |  |  |  | Doctor prescribe medicine page |  |  | create table | Doctor page |  |  | create table |  | Updata |  |  |  | 完成
32 | 12018246234 | Abel | 杨林 |  |  |  | Patient Home page |  |  |  | Patient page |  |  |  | Patient fill in information page |  |  | create table | Patient page |  |  | create table |  | Updata |  |  |  |  | 完成
33 | 12018246259 | Gina | 何宁 | Johnson | Restaurant Management |  | login page |  |  |  | login page |  |  |  | login page |  |  | create table |  |  |  | database |  |  |  | 完成
34 | 12018246240 | Carlos | 刘霞 |  |  |  | home page |  |  |  | home page |  |  |  | home page |  |  | create table | menu page | [7 empty] | 完成
35 | 12018246563 | Johnson | 安继奎 |  |  |  | register page |  |  |  | register page |  |  |  | register page |  |  | create table | About Us page | [8 empty] | 完成
36 | 12018246571 | Alan | 马智慧 |  |  |  | Reservation page |  |  |  | Reservation page |  |  |  | Reservation page |  |  | create table |  |  |  | database | [6 empty] | 完成